## DISTRICT BUDGET FORM
LHC ACTIVITY BUDGET PLANNER AND CONTROL SHEET
District/Area/Council: |  |  |  | 60-Day Benchmark Date:
Activity Title: |  |  |  | 60-Day Benchmark Attend 25%: | 0
Activity Start Date: |  |  |  | 30-Day Benchmark Date:
Activity Location: |  |  |  | 30-Day Benchmark Attend 50%: | 0
Staff Advisor: |  |  |  | 14-Day Benchmark Attend 85%: | 0
Lead Volunteer: |  |  |  | On-line Registration: | Yes |  | No
Cost Center: |  |  |  | On-line Payments: | Yes |  | No
ESTIMATED REVENUE |  |  | BUDGET | ACTUAL REVENUE |  |  |  | ACTUAL
Participant Type | Est. # Participants | Fee |  | Participant Type | Actual # Participants | Fee
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
Total Participant Fees | 0 |  | 0 | Total Actual Participants | 0 |  |  | 0
Other Income (enter description below) |  |  |  | Other Income (enter description below)
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
|  | 0 | 0 |  |  | 0 |  | 0
Total Other Income |  |  | 0 | Total Other Income |  |  |  | 0
TOTAL ESTIMATED REVENUE |  |  | 0 | TOTAL ACTUAL REVENUE |  |  |  | 0
ESTIMATED EXPENSES |  |  |  | ACTUAL EXPENSES
Program Supplies
Food & Commissary Supplies
Sanitation & Janitorial Supplies
Facility Rental Fee (including council camp rentals)
Recognition (Patches)
Equipment Rental
Printing/Postage
Expense Contingency (10% of expenses) |  |  | 0
Administration Fee (10% of total estimated revenue) |  |  | 0 | Administration Fee (10% of total estimated revenue) |  |  |  | 0
TOTAL ESTIMATED EXPENSES |  |  | 0 | TOTAL ACTUAL EXPENSES |  |  |  | 0
NET Difference + OR (-) |  |  | 0 | ACTUAL NET Difference + OR (-) |  |  |  | 0
Approvals |  |  |  | Close-Out
Lead Volunteer:___________________________ |  | Date: | _________ | Lead Volunteer:___________________________ |  | Date: |  | _________
Staff Advisor:_____________________________ |  | Date: | _________ | Staff Advisor:______________________________ |  | Date: |  | _________
Council Approval:__________________________ |  | Date: | _________ | Council Approval:______________________________ |  | Date: |  | _________
EVENT TO BE CLOSED NO LATER THAN 30 DAYS FROM DATE OF EVENT
January 14, 2021 Revision

## BACKDATER
LHC EVENT PLANNING BACKDATER
District/Area/Council: | 0
Activity Title: | 0
Activity Start Date: | 0
Activity Location: | 0
Staff Advisor: | 0
Lead Volunteer: | 0
Cost Center: | 0
Task | Days Before Event | Date Due | Person Responsible
Reserve LHC facilities (if needed) | -365 | -365
Recruit event chair | -270 | -270
Recruit event committee | -240 | -240
Recruit Short-Term Camp Administrator | -240 | -240
Complete event site appraisal (non-council sites) | -210 | -210
Develop event budget | -200 | -200
Develop event marketing and promotion plan | -200 | -200
Submit completed event approval packet (see checklist) | -180 | -180
Event Committee Meeting - develop theme and program | -180 | -180
Event Committee Meeting | -150 | -150
Confirm location (LHC sites) or Secure location (non-council sites) and permits | -150 | -150
Set up and open event registration | -120 | -120
Set up Facebook/social media event | -120 | -120
Update website | -120 | -120
Event Committee Meeting | -120 | -120
Recruit medical officer | -120 | -120
Recruit needed event staff | -120 | -120
eNews/Roundtable Save the Date/Invite | -120 | -120
Event Committee Meeting | -90 | -90
Order recognition items (patches, prizes, etc.) | -90 | -90
Prepare/distribute event flyer | -90 | -90
eNews/Roundtable Invite | -90 | -90
Begin Facebook/social media promotion | -90 | -90
Event Committee Meeting. -60 Day Registration Benchmark | -60 | -60
Order portable toilets, water buffalos, etc. | -60 | -60
Arrange for religious observance | -60 | -60
Prepare menu (if offering food service) | -60 | -60
eNews/Roundtable Invite | -60 | -60
Complete/distribute event program guide | -60 | -60
Site walk through | -60 | -60
Complete event security plan | -60 | -60
Complete event emergency procedures | -60 | -60
Boost Facebook/social media event | -45 | -45
Event Committee Meeting. -30 Day Registration Benchmark | -30 | -30
Confirm Short-Term Camp NCAP requirements | -30 | -30
Early/Discount registration deadline | -30 | -30
Confirm event staff | -30 | -30
Prepare event signage | -30 | -30
Receive dietician menu approval (if offering food service) | -30 | -30
Notify local police, fire, EMS, hospital of event | -30 | -30
Arrange traffic control and on-site communications | -30 | -30
eNews/Roundtable Reminder | -30 | -30
Event Committee Meeting. -14 Day Registration Benchmark | -14 | -14
Final Site walk through/Complete Event Safety Checklist | -14 | -14
Finalize physical arrangements, activity locations, campsites) | -14 | -14
Request insurance certificates | -14 | -14
Request any needed printing | -14 | -14
Pick up all needed materials | -7 | -7
Pick up/order food (if offering food service) | -7 | -7
Send event update/reminder email to registrants | -2 | -2
Physical set up of events | -1 | -1
Event | 0 | 0
Complete Short-Term Camp Assessment | 0 | 0
Capture photo/video at event | 0 | 0
Day of event Facebook/social media post | 0 | 0
Submit any payments collected at event | 1 | 1899-12-31
After event satisfaction survey sent | 1 | 1899-12-31
Prepare and send Thank You Notes | 2 | 1900-01-01
Submit Incident/Near Miss Reports | 3 | 1900-01-02
After event satisfaction survey reminder | 3 | 1900-01-02
After event wrap up meeting | 7 | 1900-01-06
Complete event close out (see checklist) | 30 | 1900-01-29
Formulas:
Date Due = B5+[Days Before Event]

## MARKETING PLAN
LHC EVENT MARKETING AND PROMOTION PLAN
District/Area/Council: | 0
Activity Title: | 0
Activity Date: | Begin | 0 | End
Activity Time | Begin |  | End
Activity Location: | 0
Event Summary
Event Contact Person | Name |  | Phone |  | Email
Event Registration Link
MESSAGE | DAYS OUT | DUE DATE | TARGET AUDIENCE | PERSON RESPONSIBLE | NOTES | PRIORITY
ONLINE
Registration/Website | -120 | -120 | Leaders/Parents/Scouts | District Representative |  | HIGHEST
District E-News | -120 | -120 | Leader/Parents | District Rep or Com Chair | Save the Date
| -90 | -90 | Leader/Parents | District Rep or Com Chair | Invite/Save
| -60 | -60 | Leader/Parents | District Rep or Com Chair | Invite
| -30 | -30 | Leader/Parents | District Rep or Com Chair | Reminder
SOCIAL MEDIA
Facebook Event | -120 | -120 | Leaders/Parents/Scouts | District Representative
Facebook Promotion | -90 | -90 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -60 | -60 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -55 | -55 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -53 | -53 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -51 | -51 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -49 | -49 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -47 | -47 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -45 | -45 | Leaders/Parents/Scouts | District Rep. or Mkt Team
Boosted Event | -45 | -45 | Leaders/Parents/Scouts | District Rep. or Mkt Team | 2 week boost | If budget allows
| -38 | -38 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -31 | -31 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -24 | -24 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -17 | -17 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -10 | -10 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -7 | -7 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -5 | -5 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -3 | -3 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| -1 | -1 | Leaders/Parents/Scouts | District Rep. or Mkt Team
| 0 | 0 | Leaders/Parents/Scouts | District Rep. or Mkt Team | DOE Post
PRINT MEDIA
Flyers/Invite | -90 | -90 | Leaders/Parents/Scouts | District Rep. or Mkt Team |  | Final date of completion
Event Program Guide | -60 | -60 | Leaders/Parents | District Rep or Act Chair
Optional with approval
Save the Date | -180 | -180 | Leaders/Parents/Scouts | District Rep or Mkt Team |  | If budget, time, & volunteers allow
Reminder Postcard | -45 | -45 | Leaders/Parents/Scouts | District Rep or Mkt Team |  | If budget, time, & volunteers allow
Videos | -45 | -45 | Scouts/Parents | District Rep or Volunteer |  | If budget, time, & volunteers allow
Formulas:
DUE DATE = (C5+[Begin])